## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | M - 1 | 1.Choose the data (refer to Day 3 ppt) either small, medium or large text data. 2.Read the data file (either web scrap or import as csv or txt files) 3.Store the data in the database and fetch the data. 4. Do text cleaning and Normalization 5.Using multiprocessing techniques, find the word and its counts. | MUST HAVE |  |  | 3- Completed
2 | 2 | M - 2 | 1. Sentiment analysis / Text Classification / Topic modeling 2. Store in DB 3. Apply parallelism 4. Send the summary email | MUST HAVE |  |  | 3- Completed
3 | 3 | M - 3 | 1.Load Dataset. 2.Sends each data text in parallel to an LLM or any unsupervised learning algorithm for sentiment classification/topic modelling/text classification. 3.Saves results into a CSV (or your text storage DB). 4. Mail the csv file. 5. Measure the accuracy and performance of output using traditional method / unsupervised learning method (measuring the output prediction time) | MUST HAVE |  |  | 3- Completed
4 | 4 | M - 4 | 1.Create an UI part for your project.(preferably using streamlit) | MUST HAVE |  |  | 3- Completed
Note on F1: ====== ID#AAABr3jwXbw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
M - 1 | 1 | 1.Choose the data (refer to Day 3 ppt) either small, medium or large text data. 2.Read the data file (either web scrap or import as csv or txt files) 3.Store the data in the database and fetch the data. 4. Do text cleaning and Normalization 5.Using multiprocessing techniques, find the word and its counts. | 2025-09-08 | 2025-09-17 | Adeeba Aslam | Coding | 3- Completed | 5
M - 2 | 2 | 1. Sentiment analysis / Text Classification / Topic modeling 2. Store in DB 3. Apply parallelism 4. Send the summary email | 2025-09-24 | 2025-10-04 | Adeeba Aslam | Coding | 3- Completed | 3
M - 3 | 3 | 1.Load Dataset. 2.Sends each data text in parallel to an LLM or any unsupervised learning algorithm for sentiment classification/topic modelling/text classification. 3.Saves results into a CSV (or your text storage DB). 4. Mail the csv file. 5. Measure the accuracy and performance of output using traditional method / unsupervised learning method (measuring the output prediction time) | 2025-10-06 | 2025-10-15 | Adeeba Aslam | Coding | 3- Completed | 6
M - 4 | 4 | 1.Create an UI part for your project.(preferably using streamlit) | 2025-10-16 | 2025-10-28 | Adeeba Aslam | Integration Test | 3- Completed | 5
Note on D2: ====== ID#AAABr3jwXcE Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABr3jwXbQ Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABr3jwXbU Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABr3jwXbc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABr3jwXbk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABr3jwXbo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABr3jwXcQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABr3jwXb0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABr3jwXb4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABr3jwXb8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABr3jwXbM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABr3jwXcA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABr3jwXbg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABr3jwXcM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABr3jwXbs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABr3jwXcI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABr3jwXbY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2025-09-08 | overview of project | got to know about parallel text processor
1 | 2025-09-09 | sequential processing vs parallel processing | understood the working by implementing the code
1 | 2025-09-10 | sqlite3 built in Database introduction | worked with sqlite3 database
1 | 2025-09-11 | Regukar expression concepts | learned regex concepts
1 | 2025-09-12 | dataset selection guidance, exploration | choosed a medium level tweets dataset, loaded the dataset and explored it
1 | 2025-09-15 | Dataset storing, preprocessing | Stored the data in the database and fetched the data, done text cleaning and Normalization
1 | 2025-09-16 | apply multiprocessing techniques on chosen dataset | applied multiprocessing technique and found the most common word
1 | 2025-09-17 | Milestone 1 presentations | Presented the work carried out till date as part of milestone 1
2 | 2025-09-18 | Discussed about problem statements(sentiment analysis, text classification,topic modelling) | understood the problem statements significance and relevance to my chosen dataset
2 | 2025-09-24 | email notification sending | worked on email concepts by using smtplib, email libraries of python
2 | 2025-09-26 | problem statement finalization | chosed topic modelling as my problem statement and researched about its working
2 | 2025-09-30 | prepared input for lda algorithm to perform topic modelling | converted the results( preprocessed text as string) of milestone-1 into list of tokens
2 | 2025-10-01 | lda model implementation and most dominant topic assignment | trained the lda model using corpus, dictionary and assigned the most probabble or weighted topic to each tweet
2 | 2025-10-03 | maintain results in dataset and an email alert on topic modelling summary | stored the results of topic modelling in a db by connecting to sqlLite3 and sent an email alert on its summary using smtplib, email libraries of python
2 | 2025-10-04 | Milestone 2 presentations | Presented the work carried out till date as part of milestone 2
3 | 2025-10-06 | introduced to performance metrics concept | researched about performance metrics to analyse the performance of my topic modelling task
3 | 2025-10-09 | instructed to find performance metrics for lda model(classical approach) | Implemented code to find the performance metrics for lda model
3 | 2025-10-10 | explained about time camparision concepts | performed time comparision between sequential processing and parallel processing
3 | 2025-10-11 | introduced to modern LLM or unsupervised techniques for topic modelling task | implemented modern bert algorithm for topic modelling task usin bertopic library
3 | 2025-10-13 | asked to analyze the performance of modern topic modelling technique | found the performance metrics for Bert topic modelling algorithm
3 | 2025-10-14 | finding the best model among the classical and modern approaches | done by comparing the performances of lda model and bertopic model
3 | 2025-10-15 | Milestone 3 Presentation | Presented the work carried out till date as a part of milestone 3
4 | 2025-10-16 | introduced to streamlit library | explored the streamlit library of python to add ui part for my project
4 | 2025-10-17 | explained about the tasks to be done as a part of milestone 4 | frame a rough sketch for the web application demonstarting the features to be inluded in it
4 | 2025-10-23 | develop login page for the web application | created a login and logout page to manage the sessions in the web application
4 | 2025-10-24 | develop the dataset, preprocess, word count pages | created those pages to load and preprocess the dataset and to perform the word count analysis
4 | 2025-10-27 | added lda,bert,comparision,download, email pages | done to find the best model, to export the results in csv and email formats
4 | 2025-10-28 | Milestone 4 presentations | presented the work carried out till date as a part of milestone 4
4 | 2025-10-30 | instructed to do 5 min ppt for final presentation | made a ppt by covering all things done in this internship
4 | 2025-11-03 | asked to present the ppt | gave the mock presentation with PPT, streamlit application, and agile template.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-08 | 2025-09-17 | Adeeba Aslam | begined the tasks of milestone one with basics of parallel and sequential processing | ended the task by implementing preprocessing techniques and find the most common words in the chosen dataset | no
2 | 2 | 2025-09-24 | 2025-10-04 | Adeeba Aslam | started the task by coverting results of milestone 1 into list of tokens using multiprocessing | concluded the task by sending an email summary on topic modelling | no
3 | 3 | 2025-10-06 | 2025-10-15 | Adeeba Aslam | commenced the work by understanding the performance metrics concept for unsupervised models | finished the work by implementing bert model and comparing the performances of lda and bert models
4 | 4 | 2025-10-16 | 2025-10-28 | Adeeba Aslam | started the work by understanding streamlit library of python to develop web applications at ease | ended the work by developing a fully funcationable web application to demonstrate the work done in the previous 3 milestones
5
6
7